## general_report
Key | Title/Summary | Priority | Description | Story Points | Sprint | Created
FOURTYFIVE-46 | Verify website | Must Have | As a user, I want to use a website that works seamlessly with no issues or errors. Acceptance Criteria: - All user stories function as planned as defined by their written test on a Google Chrome web browser. Tasks: -Verify “Create User Account” user story is complete -Verify “Login To Account” user story is complete -Verify “Manage User Session” user story is complete -Verify “Show Recommended Information” user story is complete -Verify “Individual Item Page” user story is complete -Verify “Anchored Navigation Bar” user story is complete -Verify “User Search” user story is complete -Verify “Admin Control Panel” user story is complete -Verify “Individual Category Page” user story is complete -Verify “User Profile” user story is complete -Verify “Saved Pages” user story is complete -Verify “Search Results Paging” user story is complete -Verify “Integrated Maps” user story is complete -Verify “Website Appearance” user story is complete -Verify “Mobile Friendly Website” user story is complete -Verify “Write User Reviews” user story is complete -Verify “Show User Reviews” user story is complete -Verify “Weather API” user story is complete -Verify “Sort Search Results” user story is complete -Verify “Remove User Account” user story is complete -Verify “Forgot Password” user story is complete -Verify “Contact Details” user story is complete | 2 | 2 | 2017-10-19 17:49
FOURTYFIVE-45 | Display Contact Details | Should Have | As a user I want to be able to see the contact details for the website to contact the people running SmartCity in case I find errors, want to provide feedback, or have general queries about the website. Acceptance Criteria: - SmartCity phone Number displayed - SmartCity email displayed Tasks: - Create new .html page which displays contact email and phone number for SmartCity - Update “Contact Us” button from search results html page to direct to new contact us html page | 1 | 2 | 2017-10-14 21:14
FOURTYFIVE-44 | Website Appearance | Should Have | As a user I want to use a website with a common theme throughout all the webpages to make the website look more professional and flow better making me trust it more. Acceptance Criteria: - All pages have the same base font - All pages have the same base colour scheme - All pages have a banner image at the top of the web page Tasks: - Edit CSS file to incorporate common theme items for all web pages - Edit all html pages to incorporate the CSS file classes | 3 | 2 | 2017-10-12 21:09
FOURTYFIVE-43 | Unit Tests | Should Have | User Story: - As a user I would like a website that works efficiently without bugs or errors. Acceptance Criteria: - Tests pass as they are intended as defined by comments or their test title - Tests are written to ensure all sections using information from the database display the correct data - Tests are written to ensure all forms submit when the correct information is entered and fail when incorrect information is entered - Tests are written to ensure that data entered or changed via forms have been correctly entered or changed in the database Task: - for all views in views.py, create tests to see if status code returned is accurate - for all views in view.py, create tests for general functionality of each view - for all models, create tests to identify if item is instantiated accurately - for all forms, create tests to ensure all information passed through is valid - for all forms, create tests to ensure all information when passed through incorrectly returns an error | 2 | 2 | 2017-10-08 16:50
FOURTYFIVE-42 | Weather API | Could Have | As a user, I'd like to know about how the weather is for the day so that I plan my journey to get there accordingly Acceptance Criteria: - Individual Item Page should request a remote weather API service using the coordinates of each place - Individual Item Page should display the information about the current weather of the place via an image/icon as well as text Tasks: Add a script to connect to a weather API service to retrieve data Add an html element that displays the weather information to users | 2 | 2 | 2017-10-07 20:01
FOURTYFIVE-41 | Mobile Friendly Website | Should Have | As a user, I'd like the website to be responsive to different devices so that I can access the website from my smartphone or tablet. Tasks: Using grid, bootstrap columns and css, ensure all pages are responsive. | 3 | 2 | 2017-10-07 19:49
FOURTYFIVE-40 | Integrated Maps | Should Have | As a user I want to see the location on a map to help me visualise where to go and where the location is. Acceptance Criteria: - Individual item page should make API call to the google API service. - Individual item page should display a google map that is zoomed in on the place with a marker of where the place is on the map - Users should be able to zoom in and out of the map. Tasks: - modify individual item page html to include google maps frame (20min) - Integrate Google Map API to individual item page(2hr) | 1 | 2 | 2017-10-05 12:24
FOURTYFIVE-39 | Individual Category Page | Must Have | As a user I want a page which displays all data inputs from one specific category (restaurants, hotels, malls, parks, museums, libraries, colleges, industries, or zoos). Acceptance criteria: - When viewing an individual category, only items from that category are displayed - Items are displayed in a list format - All items displayed have click-through links Tasks: - Create tests (30 mins) - Create html for pages (1 hr) - Create Django functionality for html pages (2hr) - Implement tests (30 mins) | 2 | 1 | 2017-10-01 14:42
FOURTYFIVE-37 | User Search | Must Have | User Story - As a user I would like to search places to show all information relating to a word or certain words I input into a search bar to make it quicker for me to find certain places. Acceptance Criteria: - The navigation bar anchored to the top of webpages will display a search bar and a search button on every page to allow me to look for places by typing keywords. - Clicking the "search" button will redirect me to the search result page showing relevant results. - The keyword entered on the search bar will be compared with the name of the places in the database - A list of places with the name containing the keyword will be displayed after the user has pressed search. - Search results will display the following: Name of destination Address of destination - The search results will be displayed in order of date added to the database. - Clicking on the result text will take the user to the individual item's page via a click through link. Tasks: 1.Inside the navigation bar, add a form using bootstrap and appropriate event handler to manage form submission and request to the server. 1. Create a search result page with function to handle response from the server 2. Write a code to retrieve the results from the database using the search keyword 3. Write a code to display the results to the search page. 3. Write a test case | 3 | 1 | 2017-08-23 10:40
FOURTYFIVE-36 | Forgot Password | Should Have | User Story: - As a user, I want to be able to change my password if I forget my account password. Acceptance Criteria: - When on the login page, a link will be displayed under the password text field which says "Forgot my password". - Clicking on 'Forgot my password’ will display a "send" button and an input field for the me to enter my login email address. - Clicking the "send" button will send the user an email with a new link which redirects the user to a password reset page which allows them to create a new password for their account. - The password reset page will display an input field for the new password and a "enter" button. - Clicking on the "enter" button will update the user's password and display confirmation message indicating that the password is reset. Tasks: - Add link to login page to begin reset password. - Create a Django form to be submit. - Add a field for inputting the address and a button for submitting the form. - Create a .html page to reset the password of the user with forms to be submitted. - Implement code to send an email to the input address with a link to the password reset page. - Verify the input details and add confirmation message. - Update user's password in the SQL database. | 2 | 3 | 2017-08-16 15:58
FOURTYFIVE-34 | Spam Filtration | Should Have | User Story: - As an admin, I want to have a "I am not a robot" checkbox for when users try to sign up so that the web system does not get spammed by robots or fake users and keeps the web system safe. Acceptance Criteria: - When a user tries to sign up for the Smart City web system, a check box which states "I am not a robot" will be displayed which users will need to check off to help reduce spam/bots on the web system. | 2 | 3 | 2017-08-09 11:34
FOURTYFIVE-33 | Validate User email | Should Have | User Story: - As a user, I want my email address to be validated so that no one else can use my email address to register to the system. Acceptance Criteria: - Only after signing up with the website's local signup form, a confirmation message should be displayed saying, "A confirmation email has been sent to your email address." - Users will receive an email from the website displaying a link labelled "Confirm your email". - Clicking on the "Confirm your email" link will redirect the user to the website's confirmation service, displaying a message stating "Your account has been confirmed" | 3 | 3 | 2017-08-09 11:30
FOURTYFIVE-32 | Remove User Account | Could Have | User Story: - As a user, I want to be able to remove my account so that I remove my personal details from the website when I decide not to use it anymore. Acceptance Criteria: - A button labelled "Delete" will be displayed on the users individual account information page when the user clicks the "edit" button. - When the delete button is pressed, the page will show confirmation page displaying "Account deleted" - The information about the user in the database such as their name, email, and password will be removed. - The user will be redirected to the welcome page in 3 seconds. Tasks: - Add button to delete account. - Write code in django to remove a user from the database. - Display confirmation message and redirect user to the welcome page | 1 | 2 | 2017-08-09 11:27
FOURTYFIVE-30 | Link to SNS | Could Have | User Story - As a user, I want to share places I found to my social network so that I can let people I know about the placed I found. Acceptance Criteria: - For every place/destination, a button labelled "Share on Facebook" will be displayed. - Clicking on the "Share on Facebook" button will create a popup window labelled "Post to Facebook". - The popup window will display the following: 1) An option to post on my timeline or my friend's timeline presented via a drop down menu. 2) A text box field to enter a user comment. 3) A "Post to Facebook" button. - Clicking on the "Post to Facebook" button will post my comment with the link to the place/destination on the website to the users Facebook timeline specified. | 4 | 3 | 2017-08-09 11:27
FOURTYFIVE-28 | SNS Sign Up | Won't Have | User Story: - As a user I want to sign up to the system using my Facebook or Google account so that I do not have to go through the registration process manually. Acceptance Criteria: - A button labelled "Sign up with Facebook" is displayed on the signup page. - Clicking on "Sign up with Facebook" redirects users to Facebook's authorisation page, that shows an authorisation button for users to click. - Clicking on the authorisation button will redirect users to the login page of the website and registers users to the system with their personal information obtained directly from Facebook. | 4 | 3 | 2017-08-09 11:25
FOURTYFIVE-27 | Show reviews/rating | Could Have | User Story: - As a user, I want to see reviews for each place so that I can make my decision based on other’s experiences Acceptance Criteria: - Individual destination/place web page should show a list of reviews. - Each review should show the username, comment, and rating. - If no reviews have been provided by users, the reviews list will be empty Tasks: - Modify view functionality to pass Review model variables into template -Modify individual item page template to display review functionality | 1 | 2 | 2017-08-09 11:24
FOURTYFIVE-26 | SNS login | Won't Have | User Story: - As a user I want to login using my Facebook or Google account so that I don’t have to remember a separate login information and go through the login process manually. Acceptance Criteria: - A button labelled "Log in with Facebook" is displayed. - Clicking on "Log in with Facebook" redirects users to Facebook's authorisation page, that shows an authorisation button for users to click. - Clicking on the authorisation button redirects users back to the homepage of the website. - The website will show the users name on the navigation bar to confirm that they have successfully logged in. | 4 | 3 | 2017-08-09 11:24
FOURTYFIVE-25 | Write User Reviews | Could Have | User Story: - As a user I want to submit reviews to places so that I can share my experience with other users. Acceptance Criteria: - On an individual item page, a comment input field, user rating radio buttons (ranging from 1 to 5) and a submit buttons should be visible. - When the submit button is clicked, a user review with the rating will be submitted, updating the list of reviews. -User will be able to submit only one review. Task - Create a new table/model called Reviews to store all written reviews, ratings and place name - Create a button on an individual item page labelled “Write Review” with associated form - Create view functionality to allow a new pop up window to appear once “Write Review” button is pressed - Create textbox which allows user input in a written review, a radio button option for values 0 – 5 to allow users to leave a rating, and a button labelled “Submit review” | 2 | 2 | 2017-08-09 11:23
FOURTYFIVE-24 | Individual Item Page | Must Have | User Story: - As a user I want to be able to view detailed information about a place so that I can get more information Acceptance Criteria: - Clicking on each item (place) will redirect me to an individual item page - A web page will display information about a selected place including google map of the place, the place name, and if it is a college category item it will display the address, email and departments of the place, or industry category item then it will display the address, email and industy type of the place, else it will display the place's phone number and email. Task : - Create unit tests for acceptance criteria - Write code to display destination's information including name, address, opening hours, contact number, and description of the place - Write client side code to handle Google Maps API - Perform unit tests/acceptance tests | 2 | 1 | 2017-08-09 11:23
FOURTYFIVE-22 | User Profile | Should Have | User Story: - As user I want to view my profile and be able to modify my account detail so that I can keep it up to date. Assessment Criteria: - The navigation menu will display a link labelled "Account Settings". - Clicking on the "Account Settings" link will redirect me to my account information page. - The page displays all information about my user profile. - The account information page displays a button labelled "Edit Information" - Clicking the "Edit Information" button will redirect me to a page for editing my account information. - The edit account page displays a form pre-filled with my personal information; including the details I registered with and additional information that I added later. - Clicking on the "update" button returns me to the account information page so that I can view the changes I have made. Tasks: - Create a .html page with a form for user account and edit button. - Add link to the navigation menu to the account page. - Write code in django to populate the account page with the current user's info from the SQL database. - Implement code in django to update the user's info in the SQL database. - Create and implement tests | 3 | 1 | 2017-08-09 11:22
FOURTYFIVE-21 | Journey planner | Won't Have | User Story: - As a user I want to there to be a function to so that I can organise and list the places I need to visit with respective times. Acceptance Criteria: - On individual item page, the google map will be updated so that user's current location and the item's address is used to generate google map's route planner. - If access to user's geolocation has not been allowed yet, display a popup asking users for their permission. - If allowed, continue with generating route planner. - If not allowed, do not generate route planner. | 5 | 3 | 2017-08-09 11:22
FOURTYFIVE-20 | Anchored Navigation Bar | Must Have | User Story: - As a user I want to have access to an anchored menu in every page so that I can navigate myself to key services whenever I want. Assessment Criteria: - A navigation menu will be anchored at the top of every webpage along with the search bar. - When I'm logged in, the navigation bar will have following links: 1. "Home" link to redirect me to the welcome page when I click on the sites logo. 2. "Admin Settings" link to redirect me to the administration control panel when I am logged in as an admin. 3. "Account Settings" link to redirect me to my account information page 4. "Saved Pages" link to redirect me to the save pages page. 5. "Contact Us" link to redirect me to the contact details page. 6. "Log Out" link to log me out of the website. - When I'm logged out, the navigation bar will only show the logo that will redirect the user to the welcome page - When I'm logged in, the navigation bar will contain a search form for me to search places matching my query. Tasks: - Create unit tests for acceptance criteria - Create drop down menu of click through links to other important pages on the website - Create "Log out" button and associated functionality to remove users session - Perform unit tests/acceptance tests | 1 | 1 | 2017-08-09 11:13
FOURTYFIVE-19 | Nearby Geolocation Search | Could Have | User Story: - As a user, I want to be able to search for places nearby my geo-location to find new places to go to around my area. Acceptance Criteria: - Next to the search bar, there should be displayed a button labelled "Use my location". - Clicking on the "Use my location" button will display a popup message asking if the user wants to use their current location on the web system, and two buttons: "Allow" and "Close" to see if the user allows the web system to access and use such information. - Clicking on "Allow" will enable the website to cache the users location information. - Once allowed, clicking on the search button will display a list all places within certain distance (10 km) from the users location. | 3 | 3 | 2017-08-09 11:12
FOURTYFIVE-18 | Search Result Paging | Should Have | User Story: - As a user, I want pagination for my search result so that I can easily use the search feature. Acceptance Criteria: - If the number of items in the search result exceeds a certain amount (10) there should be displayed a pagination that allows me to read through the results in multiple segments. - There will be buttons labelled "Previous" and "Next" which will appear next to the number so that I may click to go onto the next or previous segment of search results while seeing which page I am currently on. Tasks: - Add server side code to enable pagination | 1 | 1 | 2017-08-09 11:10
FOURTYFIVE-17 | Secure Socket Layer | Won't Have | User Story: -As a user, I want to communicate with the service securely over a SSL so that the information that I provide to the service is unknown to anyone else. Acceptance Criteria - By typing the URL of the website on a browser, users will be directed to a website with protocol of https instead of http. | 3 | 3 | 2017-08-09 11:10
FOURTYFIVE-16 | Sort Search Results | Should Have | User Story: - As a user, I want to be given the option of sorting my search results by alphabetical order instead of the default date added ordering so that I can look through the results list to find what I want easily. Assessment Criteria: - The search result page displays a radio buttons with the following sorting options: *Alphabetical *Date - Choosing "alphabetical" will sort the result alphabetically - Choosing date will sort the result such that the places added most recently to the database will be displayed first Tasks: - Add radio button menu to search result page. - Write django and javascript code to sort results from database with the specified criteria. | 1 | 2 | 2017-08-09 11:06
FOURTYFIVE-13 | Extendable System | Should Have | User Story: - As an admin, I want the control panel to have an interface to add new cities and places to the system so that in the future I can provide information for other types of users from different cities as well. Acceptance Criteria: - The database will be divided into "State" categories such as "Queensland", "New South Wales", "Victoria", "South Australia, "ACT", "Tasmania", "Northern Territory", and "Western Australia". - Initially the database will only have "Queensland" as a present "State" option. - There will be a "Add State" option for admins to add a new "State" into the database, other than "Queensland" Tasks: - Implement 'postcode' field to sign up form for users to input their website in order to quickly identify their default state - Implement model for admins to add a state to the database. | 1 | 1 | 2017-08-09 11:00
FOURTYFIVE-12 | Remove Saved Places | Should Have | User Story: - As a user I want to remove saved places from my saved list so that I can clean the list and organize to suit my interest. Assessment Criteria: - If the user presses the button labelled "Page saved" the button will revert to the button labelled "Save page". This will delete the URL from the user's SQL database. Tasks: - Write function to detect whether the user has saved the page and change the button accordingly. - Add django functionality to remove the place from the user's saved places. | 1 | 2 | 2017-08-09 10:59
FOURTYFIVE-11 | Saved Places/Pages | Should Have | User Story: - As a user I want to save places of interest so that I can easily go back and find the places again. Assessment Criteria: - Individual item page displays a button labelled "Save Page to Profile" - When "Save Page to Profile" is clicked and saves the page successfully, the button changes label to "Place Saved" - The item ID will be saved to the user's database. - The navigation menu bar displays a link labelled "Saved Places" - Clicking on the link will redirect me to the saved places page which displays a collection of my saved places. - Each saved place will be linked to its individual item page. - Clicking on each saved place will redirect me to the individual item page. Tasks: - Add button to item page. - Change text on button when clicked - Save a new row into SavedPlace model - Add a link to the navigation menu to the saved places page - Create a html page - Populate saved places page with location names of the saved locations with links to their individual item page - Add view function to add and remove Saved Place | 1 | 2 | 2017-08-09 10:59
FOURTYFIVE-8 | Administrator Control Panel | Must Have | User Story: - As an admin, I want a separate webpage with an interface for managing application data so that I can keep the service up to date and manage update/modify data quickly. Acceptance: - Administrator control panel will the Django admin control panel to allow admins to add, modify or delete data. - Modifying data in the Django admin control panel will update the corresponding values in the database. - The admin page will display database tables for categories, cities, places, states, reviews, saved places, industries, departments and users. - All data entered by users or admins can be viewed via the admin page. - Each table will contain a form with fields for the admin to fill out. Tasks: 1. Modify the Django admin control panel page to display the required database tables and fields 2. Link admins to the control panel via a link only visible to them on the navigation bar. 3. Add model data to ensure that data input is correct. 4. Write tests 5. Verify the story is complete using the acceptance criteria | 2 | 1 | 2017-08-09 10:56
FOURTYFIVE-7 | Administrator Account Creation | Must Have | User Story: - As an admin, I want to be able to create other admin accounts so that more administrators can maintain the website as the application become larger and harder to maintain. Acceptance: - Admins will be able to create other admin users through the Django admin control panel. - if a non-admin user requests the admin control panel they will be denied access. - An error will be displayed and the request will be denied if the admin registration request is made by a non-admin user. - Admins will be able to edit user info from the control panel. Tasks: 1. Write code to add additional user information tables to the Django admin control panel. 2. Add model data to ensure correct information is input 3. Write Tests 4. Verify story is complete | 2 | 1 | 2017-08-09 10:54
FOURTYFIVE-5 | Manage User Session | Must Have | User Story: - As a user, I want to stay logged in for the duration of my usage of the service so that I don’t have to login every time I’m redirected to a new page or reloading a page. Acceptance: - Upon logging in to the website, my session is stored. - The header navigation bar will display my username as long as I am logged in so that I know that I'm logged in. - Clicking on the "log out" link on the navigation bar will log me out and end the session. - Leaving the application without logging out will still keep the session alive. Tasks: - Write code to configure and manage user’s session - Write code to add the user's name to the header navigation bar while the session is active | 1 | 1 | 2017-08-09 10:53
FOURTYFIVE-4 | Login to Account | Must Have | User Story: - As a user I want to be able to login to the website so that I can begin to use its service and access its data. Acceptance: - The welcome page displays a form with a "Login" button, username input field and password input field. - An error message will be displayed if I login with incorrect login details. - Upon successful login, the page will refresh and display the home page for a logged in user and recommended information. Tasks: - Create login form for users to specify their details. - Write client-side code to handle input validation and request response from the server - Write client-side code to handle request from the login form and establish user session - Write unit tests - Perform unit tests | 2 | 1 | 2017-08-09 10:52
FOURTYFIVE-3 | Create User Account | Must Have | User Story: - As a user, I want to create an account on SmartCity so that I am able to use its services and functionality. Acceptance: - The welcome page displays a form with a "submit" button, drop-down menu, and input fields (username, email, first name, last name, password, address, phone number, and postcode) The drop-down menu will allow the user to select their user account type and will have the options of: student, businessman, tourist. - If I submit the form with invalid input, an error message will be displayed under each invalid field to indicate that I need to correct it before submitting. -Username is considered invalid if no username has been entered or the username already exists in the database. -Email is considered invalid if it does not have the correct email format(email format must contain an "@" symbol as well as a "." symbol) -Password is considered invalid if no password has been entered. Postcode is considered invalid if no number has been entered. - Clicking on the "submit" button will register my details to the database Tasks: - Write unit tests for acceptance criteria - Create user sign up form - Create client-side code for validation and request response from the server - Write client-side code to handle request from the signup form and add new users to the database - Perform unit tests | 2 | 1 | 2017-08-09 10:50
FOURTYFIVE-1 | Show Recommended Information | Must Have | User Story: - As a user I want the website to show information primarily about information relevant to my account type (ie: if I am a student, I want to see colleges, libraries and the city so that I know where to go to further my study. If I am a tourist, I want the website to show information primarily about hotels, parks, zoos and the city so that I can quickly access information about the key destinations and places that I want to go. If I am a businessman, I want the website to show information primarily about industries, hotels and city so that I can quickly access information about the places that I want to go.) Acceptance: - If I'm logged in, the welcome page displays a collection of recommended places for my user type. - If I'm logged in as a student, a list of colleges, libraries and city information should be displayed - If I'm logged in as a businessman, a list of hotels, industries and city information should be displayed - If I'm logged in as a tourist, a list of hotels and city information should be displayed. Tasks: - Create unit tests for acceptance criteria - Create individual category buttons to show primary information based on reading user's session type and JQuery - Create recommended click through links for randomised destinations based on user's session type - Perform unit tests/acceptance tests | 3 | 1 | 2017-08-09 10:20